## About the Program
This project identifies and recognizes teachers who make a difference beyond the walls of their classrooms by encouraging students to be part of community programs, conserve nature and the environment, and educate them to be responsible citizens. This is a pilot project where we identify 10 teachers across India who will be provided Rs.1,500 per month for 12 months. They are welcome to use 1/3rd of the amount for their professional development and utilize the rest for projects, creating educational content, buying materials related to education, hosting workshops on topics such as – sustainability, sex education for boys and girls, social responsibility, and social etiquette. This project is found to be beneficial anywhere around the world. The scholarship amount will depend on the geographical location. Currently we are estimating $25 per teacher/month in India and $150 per teacher/month in the U.S.

## Process and Plan
Steps | Title | Goal | Action Items | Status | Role | Timeline | Cost/Budget | Additional Notes
1 | Program | Finalize the key aspects of the program | Brainstorm the idea, | Complete | Jeslin/Sujith/ | Jan-March 2017 | 0
|  | Identify a school that low income students attend | Research Similar Programs if any | Complete | Jeslin/Sujith/ | Jan-March 2017 | 0
|  | Work with the principal to identify a teacher | Identify a school that low income students attend | Complete | Jeslin/Sujith/ | Jan-March 2017 | 0
|  |  | Invite applications | Complete | Jeslin/Sujith/ | Jan-March 2017 | 0
|  |  | Make sure no there is no discrimination to identify teachers |  |  |  | 0
2 | Budget | Create a budget | Finalize the list of teachers | On-going | Jeslin | 2017-04-01 | 0 | 1 Teacher identified
|  |  | Finalize the amount of scholarship per month | Complete | Jeslin | 2017-04-01 | 200 | Rs. 1500 a month
3 | Award | Award the 1st schoalrship at a function | Work with school authorities to facilitate a function | Complete | Jeslin | 2017-06-01
Need to check if everything is current with Nevada state
Need to have all existing paperwork in one place
Need to look at research International NGO Status
Ability to get paid - paypal
4 | Status | Identify more teachers | Periodically check student progress | On-going | Suja Teacher
|  | Need to check if everything is current with Nevada state | Identify other areas where we can support the students | On-going | Suja Teacher
|  | Need to have all existing paperwork in one place | Continue to inspire them and provide additional training as required | On-going | Suja Teacher
|  | Need to look at research International NGO Status | Get involved with their families | On-going | Suja Teacher
|  | Ability to get paid - paypal | Surprise gifts | On-going | Suja Teacher
5 | What's Next | Use this model to inspire others in the community to support students | Share the project with other individuals who may do similar projects in their town | Pending | I-believe
|  |  | Continue the same program for 2018 and 2019 | Pending | I-believe
|  |  | Get involved with these children's future | Pending | I-believe
|  |  | Prepare a public information campaign to inspire others | Pending | I-believe